## Slide 1
An orientation to the Department of Information Technology’s (DoIT)
Project Certification process.
Project Certification Process
EPMO Mission: Enabling successful information technology initiatives and supporting business objectives.
March 2023

## Slide 2: Project Certification Committee: Content
The following Project Certification Committee (PCC) processes are presented in this document:
  Purpose
  Schedule
  Technology Exceptions
  Technical Architecture Review Committee
  PCC Committee and Agency Participants
  Agency Responsibilities
  Gates and Phases
  Presentation
  Certification
  Monthly Reports
  IV&V

## Slide 3: PCC: Purpose
The Project Certification Committee (PCC) evaluates project readiness and ensures that projects satisfy criteria established by the DoIT Cabinet Secretary-State Chief Information Officer (CIO).
PCC applies to certification of information technology projects undertaken by executive agencies meeting one or more of the following criteria in order for IT project funds to be released in a phased manner, regardless of the source of funds:
  project is required to undergo phased certifications as a result of the appropriation or grant;
  project is a subsequent or interrelated project to a previously certified project;
  project cost is equal to or in excess of $100,000.00;
  project is one deemed appropriate by the DoIT Cabinet Secretary, who is also the State CIO.
One example of a project required to undergo PCC as a result of the appropriation, is a project funded through the computer systems enhancement fund, also known as C2.
Even if a C2 project amount is less than $100,000.00, the project must be certified or a Request for Project Certification Exception and Waiver Form must be completed, emailed to Exception.Requests@doit.nm.gov and approved by the Exception Request Committee.

## Slide 4: PCC: Schedule
PCC is currently held via Teams and is scheduled on the 4th Monday of the month and begins at 9:00 am. The exceptions are the November and December meetings, which are held on the 3rd Monday of the month.
When PCC is onsite, it is held at the NM State Capitol, unless otherwise stated on the meeting invitation and agenda.
All PCC documentation must be emailed to epmo@doit.nm.gov by the scheduled date in the month you are attending PCC.
A copy of the FY23 schedule is included on the next slide and is posted on the DoIT EPMO website in the PCC and TARC Schedule section.
To schedule, please email epmo@doit.nm.gov at least two weeks prior to the date documents are due.
PCC Documentation is reviewed and returned to you by the following week with feedback, comments or questions for you to address.
Finalized documentation with all track changes accepted or rejected and all comments removed are due by 5pm on Friday, allowing Monday for a final review and posting to the DoIT EPMO website.

## Slide 5: PCC: FY23 Schedule

## Slide 6: PCC: TARC for Cloud-Based & Hosted Solutions
There are additional requirements that must be completed and approved by DoIT if the project’s IT solution deviates from the standard State system architecture.
If the project technology you select is hosted or cloud-based, please email your EPMO assigned project manager or epmo@doit.nm.gov upon your selection and prior to soliciting a solution via a request for proposal (RFP) or an IT Agreement contract.
The email should include the name of the project and the technology with a description, cost of the solution and the system implementer, if applicable.
Once the architecture is known and the solution can be fully described and illustrated and prior to certifying for Implementation phase, a completed System Hosting Evaluation Questionnaire must be emailed to exception.requests@doit.nm.gov.
The purpose of the System Hosting Evaluation Questionnaire is for the agency to present the information and diagrams related to the architecture, data and security components of the selected solution.
Approval of the System Hosting Evaluation Questionnaire fulfills the requirement for the Technical Architecture Review Committee (TARC) and approval to proceed to the Implementation Phase.

## Slide 7: PCC: TARC for Non-Cloud-Based & Non-Hosted Solutions
For any certified project that is not a cloud-based or hosted solution, the required TARC documentation is a Power Point presentation.
  The TARC presentation template includes topics and illustrations requested from each of the TARC documents previously required, such as:
  A summarized project overview & scope and details on what will be purchased as part of the solution
  A diagram of the software architecture and hardware architecture
  Information on data including type, data exchanges, applicable laws, ownership
  Security requirements such as intrusion detection, firewalls, encryption
  Monitoring and review of security logs/alerts
  End user and operational support
  Information on business continuity/disaster recovery
  Contractor agreements
  The TARC meeting is scheduled for one hour.
  The presentation, should not exceed 30 minutes, allowing 30 minutes for discussion and questions from the TARC.
  Once TARC is approved, an agency may proceed to PCC to complete the Implementation Phase requirements.

## Slide 8: PCC: Committee and Agency Participants
The DoIT Cabinet Secretary-State CIO serves as the PCC chair.
PCC members consist of the DoIT Deputy CIO, DoIT General Counsel, DoIT Chief Information Security Officer, DoIT Application Development Manager, DoIT EPMO Director, DoIT Special Projects Manager and IT and finance representatives from the Public Regulations Commission, Taxation and Revenue Department, State Purchasing Division, Department of Finance and Administration (DFA) and the Legislative Finance Committee (LFC).
Agencies must be represented by the executive sponsor, project leads and a business representative.
Prior to scheduling for PCC, the agency must ensure adequate planning appropriate to the certification gate requested and ensure that the required documentation is completed.

## Slide 9: PCC: Agency Responsibilities
    The agency must appoint a qualified lead project manager (PM).
    If the agency hires a contract PM, the CIO or lead project manager is responsible for ensuring that the contracted PM is managed in the best interests of the state and is knowledgeable in completing the DoIT PCC and TARC documentation.
    Upon DoIT request, the PM must provide access to all project management deliverables such as project plans, project schedules, initial and periodic risk assessments, quality plans and strategies, periodic project reports, requirements and design documents.
    The PM must prepare and submit a monthly status report by the 10th of each month.
    There is an Excel template for the monthly status report that is in the Project Monthly Report section.
    The PM must include independent verification and validation (IV&V) as part of the project or request a waiver using the Request for Project Certification Exception-PCC-IV&V-TARC Waiver form on the DoIT EPMO website in the Oversight and Exception Process section.

## Slide 10: PCC: Agency Responsibilities
    Review the PCC schedule ahead of time to plan project certification attendance to ensure that phase and funding approval is conducted in time to not disrupt the project.
    Do not plan on attending PCC and TARC in the same month for the same project.
Certification Request Forms for each of the project phases including Initiation, Planning, Implementation, Closeout and Change, can be found on the DoIT EPMO website in the Certification Request Forms section.
Charter and Project Management Plan templates are available on the DoIT EPMO website in the Project Certification Templates section.
The Gates and Phases section that follows, illustrates each phase and the documentation required to certify for each phase.

## Slide 11: PCC Gates and Phases

## Slide 12: PCC Gates and Phases: Initiation
Initiation Certification and Phase funding is requested by an agency for use in initial project setup activities such as defining governance, stakeholders, project objectives, high level scope, approach/phases, project charter, conducting research and analysis, procurement planning, developing Independent Verification and Validation (IV&V) plan and contract; developing initial project management plan with rough order magnitude estimates, etc.
Note: Waiver of the IV&V requirement requires specific written approval by the DoIT Cabinet Secretary.
Required Documentation: The Initiation Request for Certification and Release of Funds form, Project Charter and a presentation.

## Slide 13: PCC Gates and Phases: Planning
Planning Certification and Phase is requested by an agency to request funds needed to complete all planning needed to successfully accomplish project objectives.
This request is for activities such as procuring project manager or business analyst services to assist with planning, defining & baselining, scope, schedule, budget, quality metrics, requirements, business processes, plans for procurement, communication, change management, risk/issue management, project management (PMP), technical planning, system design, security planning, business continuity/disaster recovery planning, etc.
IV&V consultant should be engaged early on during the Planning Phase.
Required Documentation: The Project Planning Request for Certification and Release of Funds, Project Charter (if an update is needed), PMP and a presentation.

## Slide 14: PCC Gates and Phases: Implementation
Implementation Certification and Phase is for project execution. Prior to certifying for Implementation, once the technical solution has been selected, the project must be approved or waived by the TARC.
This request is for funds needed to execute, track and manage actual work of the project/phase in accordance with plans. Typical activities could include joint application design sessions, procurements (RFPs, contracts, etc.), contract and vendor management, build, buy, modify, configure, implement, testing, training, rollouts, transition to operations, etc.
The project should have a qualified PM structure to manage, track, monitor and report on progress.
IV&V consultant should be actively engaged in the project with IV&V reports delivered to the agency and EPMO@doit.nm.gov.
Required Documentation: The Implementation Certification Request, updated/final PMP, a presentation and the most recent IV&V report.

## Slide 15: PCC Gates and Phases: Closeout, Change or Update
Closeout Certification and Phase is the termination or completion of the project. Prior to Closeout, all procurements must be closed.
Required Documentation: The Project Closeout Certification Request and a presentation. Closeout Certification must include lessons learned and any benefits realized.
Change Request may be requested anytime during the project and may include changes to baselined scope, schedule, budget, project phase, technical solution or other critical changes in the project, including when additional funds become available, etc.
Required Documentation: The Change Request for Certification and Release of Funds, a presentation and an updated PMP. A results update should be included in the certification request description that includes lessons learned and performance improvements realized in the completed phases.
An Update is normally requested by the PCC but may be provided by the agency at any time during the project to report on progress.
Required Documentation: A presentation.

## Slide 16: PCC: Presentation
Include the following items in your presentation:
  Cover slide including the project name, phase being requested, names and roles of the team presenting and the PCC date
  Agency mission, project stakeholders and governance (for Initiation phase)
  An overview that includes business need, project objectives, planned technical and procurement approach (All phases)
  Work performed to date and the work to be performed in the phase being certified (All phases)
  Appropriation history, certification history, project and product deliverables with timeline, estimated project budget, and procurement information (All phases)
  Include latest IV&V summary and identify technical and security approach, risks, issues and mitigation strategies (Planning, Implementation)
  Performance metrics improvements and/or benefits realized, IV&V summary, scope verification, schedule and cost comparison, transition to operations, lessons learned (Closeout)
Include a subject matter expert who can speak in detail regarding the technical and business aspects of the project and a representative from the business side who is very familiar with the project and how the end users will utilize it.

## Slide 17: PCC: Presentation
For onsite meetings, arrive 15 minutes prior to your assigned time and take a seat in the audience area.
Bring 12 printed copies of the presentation and certification request to the hearing to be delivered to EPMO staff, who will hand them out to the committee.
Plan to present for no more than 20 minutes, allowing 10 minutes at the end of your presentation for PCC questions.
Please wear business attire and when called to present, take a seat at the hearing table.
Begin your presentation by addressing the chair first, then members of the committee. “Mr. Chairman and members of the committee…” then continue by introducing yourself and the presenters.
The same protocol is used when responding to questions from the committee. “Mr. Chairman and members of the committee…” then the response.
After you complete your presentation and respond to questions, the chair will make a motion to vote and the PCC will pass or deny the project with two votes.
For DoIT Project Certifications, the DoIT Cabinet Secretary-State CIO recuses himself from the certification vote and a non-DoIT designee serves as Chair.

## Slide 18: PCC: Presentation
For offsite meetings, you will receive a Teams invitation via Outlook.
If you are unfamiliar with the technology, the invitation is available a half hour prior to the meeting start time.
Arrive 5 minutes prior to your assigned time and be prepared to launch your finalized PCC presentation.
Plan to present for no more than 20 minutes, allowing 10 minutes at the end of your presentation for PCC questions.
Begin your presentation by addressing the chair first, then members of the committee. “Mr. Chairman and members of the committee…” then continue by introducing yourself and the presenters.
The same protocol is used when responding to questions from the committee. “Mr. Chairman and members of the committee…” then the response.
After you complete your presentation and respond to questions, the chair will make a motion to vote and the PCC will pass or deny the project with two votes.
For DoIT Project Certifications, the DoIT Cabinet Secretary-State CIO recuses himself from the certification vote and a non-DoIT designee serves as Chair.

## Slide 19: PCC: Certification
Upon PCC Approval and Certification, DoIT will issue a letter to DFA, your cabinet secretary and CIO authorizing the release of funds with either:
Release of Funds - No requirements or contingencies.
Release of Funds with Requirements - Agency will receive the released funds, however, Agency must complete the requirements or the project will be halted.
Release of Funds Contingent Upon Completed Tasks - Agency must first complete the required contingencies prior to the release of funds.
For projects with a contingency, the project is included in the original letter and a subsequent letter will be sent once the contingency has been met.
The certification letters for each month are posted on the DoIT EPMO website in the Project Certification Committee section.

## Slide 20: PCC: Monthly Reports
For all certified projects, a monthly project report is due to EPMO@doit.nm.gov on the 10th of each month after project Initiation through project Closeout. For example, if you certify a project at the April PCC, a report will be due May 10. If you certify a project for Closeout, the final report is due on the 10th of the month following your Closeout presentation.
The Project Monthly Report Template is on the DoIT EPMO website in the Project Monthly Report section.
  Sheet One is the overall monthly status of project and key performance indicators
  Sheet Two is a detailed breakdown of milestones and progress
The data to be reported is from the previous month. For example, the June 10 report contains project activities from May.
The EPMO team reviews the reports along with IV&V reports and other project artifacts to assess project health and to provide assistance & guidance, as necessary to ensure successful outcomes.
Data from these reports are posted on a quarterly basis to the DoIT EPMO website in the EPMO Project Portfolio section. Projects with the highest dollar value or high risk/visibility are displayed in the Top Ten.

## Slide 21: PCC: IV&V
The DoIT requires all certified projects engage an IV&V contractor unless waived.
IV&V means the process of evaluating a project to determine compliance with specified requirements and the process of determining whether the products of a given development phase fulfill the requirements established during the previous stage, both of which are performed by an organization independent of the lead agency.
If you are considering an IV&V waiver, please complete a Request for Project Certification Exception or Waiver form, which can be found on the DoIT EPMO website and email it to Exception.Requests@doit.nm.gov.
The form must include a strong justification for IV&V not being needed and a description of any verification and/or validation that will occur.
Since IV&V services are expected to be active early in planning, please make your request prior to certifying for the Planning Phase.

## Slide 22: PCC: IV&V
To be considered for an IV&V waiver approval, requested with a Request for Project Certification Exception or Waiver form, a project must be proven to be low risk because of the scope, technology type or the agency’s or vendor’s expert knowledge of the technology. Possible reasons for waiver approval may include:
  Projects under the $100,000 certification threshold
  Projects whose only objective is to conduct research, analysis or discovery
  Projects that are operational in nature, such as a large implementation of end user hardware components
  Projects that are related to existing SHARE functionality
  Projects for which the agency has a demonstrated mastery of a technology platform or application
  Projects with agency staff experienced in project management, business analysis, software development/integration and business operations with documented project management procedures and controls
  Projects based on mature proven technology, previously successful implementations that are similar in scope with well-defined and documented repeatable processes, managed by onsite expertise that have extensive expertise related to the project

## Slide 23: PCC: IV&V
IV&V Guidance & Template is available on the DoIT EPMO website in the IV&V Template section.
Quality Assurance IV&V Guidelines
Memo on IV&V Reporting Template
When vendors have completed their reports, instruct them to email them to your agency contact and to include EPMO@doit.nm.gov.

## Slide 24: Useful Links
DoIT EPMO website: Compliance and Project Management - New Mexico Department of Information Technology (nm.gov)
PCC webpage: Project Certification Committee - New Mexico Department of Information Technology (nm.gov)
Templates for PCC: Compliance and Project Management - New Mexico Department of Information Technology (nm.gov)
Templates for other project documents: Project Management Templates & Guidance - New Mexico Department of Information Technology (nm.gov)
Contract Templates: Contract & RFP Templates & Guidance - New Mexico Department of Information Technology (nm.gov)
Enterprise Portfolio Reports & Presentations: Project Portfolio - New Mexico Department of Information Technology (nm.gov)
For any questions, please contact your assigned EPMO project manager or epmo@doit.nm.gov